## Sheet1
Bug ID | Title | Steps | Excepted | Actual | Severity | Priority | Status
BUG001 | Password Reset fails for valid username | 1. Open Forgot Password page 2. Enter valid username 3. Click Reset | Password reset message should be displayed | Page keeps loading and then displays "504 Gateway Time-out, nginx/1.18.0 (Ubuntu)" error | High | High | Open
BUG002 | Password Reset works with invalid username | 1. Open Forgot Password page 2. Enter invalid username 3. Click Reset | Appropriate error message should be displayed | Password Reset page/message is displayed instead of an error message | Medium | High | Open
BUG003 | User can access Dashboard using browser Back button after logout | 1. Login with valid credentials. 2. Click Logout. 3. Press the browser Back button. | Dashboard should not be accessible after logout. User should be redirected to the Login page or shown an access denied message. | Dashboard page is accessible after logout using the browser Back button. | High | High | Open
BUG004 | Submitted timesheet can be modified directly after submission | 1. Submit the timesheet. 2. Reopen the submitted timesheet. 3. Try to edit the submitted entries. | User should not be able to modify the submitted timesheet directly. The submitted timesheet should become read-only. | User is able to modify the submitted timesheet directly after submission. | High | High | Open
BUG005 | Partial username search does not display matching usernames | 1. Navigate to the User Search page. 2. Enter a partial username (e.g., enter "Adm" for username "Admin22"). 3. Click the Search button. | Matching usernames containing the entered partial text should be displayed. | Matching usrnames were not displayed after performing the partial username search. | Medium | Medium | Open
BUG006 | No message displayed when searching with an invalid keyword | 1. Enter an invalid keyword in the search field. 2. Click the Search button. | A "No matching records found" message should be displayed. | No message was displayed when the invalid keyword search returned no results | Low | Medium | Open
BUG007 | Validation message is not displayed when posting empty content | 1. Navigate to the Buzz module. 2. Leave the post content field empty. 3. Click the Post button. | A validation message should be displayed indicating that the post content cannot be empty. | No validation message was displayed when the user attended post with empty content. | Medium | Medium | Open